## Product_Backlog
Design and set up the product backlog and sprint
Product_backlog_id | User_Story_id | Feature/Task | Priority | Assinged To | Complexity | Status | Remarks | Category
pb_1 | us_1 | User authentication and registration (e-commerce) | High | Backend Team |  | To Do |  | E-commerce
pb_2 | us_2 | Interactive learning dashboard | High | Fronted team |  | To Do |  | E-learning
pb_3 | us_3 | Course creation and management for instructors | High | Backend Team |  | To Do |  | E-learning
pb_4 | us_4 | Real-time chat for support or in-game interaction | Medium | Backend Team |  | To Do |  | Cross-feature

## Sprint1
Product Backlog ID | User Story ID | User Story | Task Description | Complexity | Assigned To | Estimate Time | Actual Time | Status
pb_1 | us_1 | As a user, I want to register and log in using my email and password, so I can securely access my account. | 1. User Authentication and Registration: - Design database schema for user accounts. - Implement backend APIs for registration and login (JWT-based authentication). - Create frontend forms for registration and login. - Add validation and error handling for user inputs. | Medium | Backend Team | 21 hrs |  | To Do
pb_2 | us_2 | As a student, I want an interactive dashboard that shows my courses and progress, so I can track my learning easily. | 2. Interactive Learning Dashboard: - Design the dashboard UI with course list and progress bars. - Fetch data from backend APIs - for enrolled courses and progress. - Implement sorting and filtering options for the course list. - Add real-time progress updates for ongoing courses. | High | Frontend Team | 14 hrs |  | To D

## Sprint2
Product Backlog ID | User Story ID | User Story | Task Description | Complexity | Assigned To | Estimate Time | Actual Time | Status
pb_3 | us_3 | As an instructor, I want to create and manage courses, so I can provide learning materials to students. | 1. Course Creation and Management for Instructors: - Design a database schema for courses, modules, and materials. - Develop backend APIs for creating, editing, and deleting courses. - Build a user-friendly frontend form for instructors to manage course content. - Add validation for course input fields (e.g., title, description, duration). | High | Backend Team | 10 hrs |  | To Do
pb_1 | us_4 | As a user, I want to receive confirmation emails after registration, so I know my account is successfully created. | 2. Confirmation Emails: - Integrate email service (e.g., SendGrid or SMTP) for account-related notifications. - Create email templates for registration confirmation. | Medium | Backend Team | 28 hrs |  | To Do

## Sprint3
Product Backlog ID | Product_Backlog_id | User Story ID | User Story | Task Description | Complexity | Assigned To | Estimate Time | Actual Time | Status
4 | pb_4 | us_4 | As a user, I want a real-time chat feature, so I can communicate with support or other users without delays. | 1. Real-Time Chat: - Set up WebSocket server or use a service like Firebase Realtime Database. - Design chat UI for user support or in-game interaction. Implement backend APIs for storing and retrieving chat logs. | High | Backend & Frontend Teams | 14 hrs |  | To Do
2 | pb_3 | us_3 | As a student, I want to see alerts on the dashboard when new courses are added, so I stay updated. | 2. Dashboard Alerts: - Add notification area on the interactive dashboard. - Fetch and display alerts when new courses are added to the system. - Implement push notifications for immediate updates. | Medium | Frontend Team | 10 hrs |  | To Do