## Test Plan
Section | Details
Test Plan Name | OrangeHRM Functional and Non-Functional Testing
Objective | Validate the features and functionality of OrangeHRM, ensuring it meets business requirements and works as intended.
Scope | Test the following modules: - Employee Management - Leave Management - Recruitment - Time and Attendance
Test Strategy | Types of testing to be conducted: - Functional Testing - Integration testing - Regression Testing - Performance Testing - Security Testing
Test Deliverables | - Test Plan Document - Test Cases - Bug Reports - Test Summary Report
Roles and Responsibilities | - Test Manager: Oversees testing activities. - Test Engineers: Write and execute test cases. - Developers: Fix bugs identified during testing.
Test Schedule | - Test Planning: [Start Date] to [End Date] - Test Case Development: [Start Date] to [End Date] - Test Execution: [Start Date] to [End Date] - Bug Fix and Retesting: [Start Date] to [End Date]
Risk Analysis | Risks to consider: - Unavailability of test data - Tight deadlines - Lack of resources - Incomplete requirement specifications
Entry Criteria | - Test environment setup completed. - Test data prepared. - Approved test cases available.
Exit Criteria | - All test cases executed. - No critical bugs are open. - Test Summary Report reviewed and approved.
Reporting | - Daily status reports. - Final test execution summary with bug logs and defect analysis.

## TC Dev Admin
Test Case ID | Test Scenario | Test CaseDescription | Preconditions | Test steps | Test Data | Expected Result | Actual Result | Test Status | Priority | Assosiated Req. ID | Date of Execution | Comments
TC001 | Login to Admin Page | Test login functionality for Admin | Admin account exists in the system | 1. Open OrangeHRM Admin Page 2. Enter valid admin username 3. Enter valid password 4. Click the Login button | Admin credentials | Admin user successfully logs in | As expected | Passed | High | REQ001 | 2024-12-18 | Login page works as expected.
TC002 | Add User | Test adding a new user | Admin user logged in | 1. Go to "Admin" tab 2. Click "Add" button 3. Fill in required fields (username, password, role, etc.) 4. Click Save | Username: testuser Password: Test@123 | New user is added successfully, and confirmation message is displayed | As expected | Passed | High | REQ002 | 2024-12-18 | Works correctly; check for edge cases.
TC003 | Search for a user | Test searching for an existing user | Admin user logged in, user exists | 1. Go to "Admin" tab 2. Enter username in search bar 2. Click search | Username: testuser | User details are displayed correctly | User not found | Failed | Medium | REQ003 | 2024-12-18 | Bug: User exists but search fails.
TC004 | Delete user | Test deleting a user | Admin user logged in, user exists | 1. Go to "Admin" tab 2. Search for the user 3. Select the user 4. Click Delete and confirm | Username: testuser | User is deleted successfully and no longer visible in the user list | As expected | Passed | High | REQ004 | 2024-12-18 | Ensure audit logs reflect deletion.
TC005 | Edit user details | Test editing an existing user’s details | Admin user logged in, user exists | 1. Go to "Admin" tab 2. Search and select user 3. Edit fields (e.g., email, role) 4. Click Save | Updated Email: user@test.com | User details updated successfully | As expected | Passed | High | REQ005 | 2024-12-18 | Ensure mandatory fields are validated.

## TC Dev Recuriment
Test Case ID | Test Scenario | Test Case Description | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Test Status | Priority | Severity | Test Type | Associated Requirement ID | Date of Execution | Comments/Remarks
TC001 | Add a Job Vacancy | Test adding a new job vacancy in the recruitment module | Admin user logged in | 1. Navigate to "Recruitment" tab 2. Click "Vacancies" 3. Click "Add" button 4. Fill in job title, description, and hiring manager details 5. Click Save | Job Title: Software Engineer Hiring Manager: John Smith | Job vacancy is added successfully, and confirmation message appears | As expected | Passed | High | Major | Functional | REQ101 | 2024-12-18 | Works correctly; test more roles.
TC002 | Search for a Candidate | Test searching for a candidate in the recruitment module | Candidate profiles exist in the system | 1. Navigate to "Recruitment" tab 2. Enter candidate name in the search bar 3. Apply any filters (e.g., status, job title) 4. Click Search | Candidate Name: Jane Doe | Candidate profile is displayed with accurate details | As expected | Passed | Medium | Major | Functional | REQ102 | 2024-12-18 | Add more test cases for filters.
TC003 | Apply for a Job Online | Test online job application submission | Job vacancy is available online | 1. Navigate to the OrangeHRM career portal 2. Select a job vacancy 3. Fill in application form 4. Attach resume and other documents 5. Click Submit | Candidate Name: John Doe Resume: Resume.pdf | Application submitted successfully, and confirmation email sent | As expected | Passed | High | Critical | Functional | REQ103 | 2024-12-18 | Ensure resume upload accepts all formats.
TC004 | Edit Candidate Details | Test editing candidate information | Admin user logged in | 1. Navigate to "Recruitment" tab 2. Search and select a candidate 3. Click Edit 4. Modify details (e.g., status, remarks) 5. Click Save | Status: Shortlisted | Candidate details updated successfully | As expected | Passed | Medium | Major | Functional | REQ104 | 2024-12-18 | Ensure audit trail reflects changes.
TC005 | Delete a Job Vacancy | Test deleting an existing job vacancy | Job vacancy exists | 1. Navigate to "Recruitment" tab 2. Go to "Vacancies" 3. Search for a vacancy 4. Select the vacancy 5. Click Delete and confirm | Job Title: Software Engineer | Job vacancy is deleted successfully, and it is removed from the list | As expected | Passed | High | Critical | Functional | REQ105 | 2024-12-18 | Test for dependent entities like candidates.

## Test Summary
Module/Feature | Total Test Cases | Executed | Passed | Failed | Blocked | Not Executed | Pass Percentage | Remarks
Employee Management | 50 | 50 | 48 | 2 | 0 | 0 | 96% | Retesting in progress.
Leave Management | 40 | 40 | 39 | 1 | 0 | 0 | 97.5% | Critical issue fixed.
Recruitment | 30 | 28 | 25 | 2 | 1 | 2 | 89.3% | Pending bug resolution.
Time and Attendance | 20 | 20 | 20 | 0 | 0 | 0 | 100% | Module is stable.
Performance Module | 25 | 23 | 22 | 1 | 0 | 2 | 95.7% | Minor UI issues found.
Overall Total | 165 | 161 | 154 | 6 | 1 | 4 | 95.65%

## Test Metrics
Metric | Value | Remarks
Test Case Execution Rate | 95% | Most planned test cases executed, pending ones due to dependency issues.
Defect Detection Rate | 12% | Indicates moderate defect discovery; focus needed on Payroll and Recruitment modules.
Pass Percentage | 93% | High-quality testing with minor issues.
Defect Fix Rate | 90% | Majority of critical defects resolved.
Defect Leakage | 4% | Minimal defects escaped to UAT phase.
Automation ROI | 130% | Significant savings achieved from automated regression tests.